## Sheet2
Discovery Center Exhibits. Challenge Cost Share Grant 20100909
Volunteer Hours
| Status as of 15Dec13 | Assignment | Money Spent | Ed Barrios | Marty Cornell | Mickey Dufilho | Phil Huxford | David Plunkett | Krissy Plunkett | Total Hours
Planning and Administration |  |  |  | 2 | 2 | 2 | 1 | 2 |  | 9
Rollup shutters for Info. Shelter | Three shutters installed. Trimwork still to do | Phil Huxford | 1760
Interpretive signs for Big Slough Boardwalk | No Activity | Tom Schneider
Interpretive signs for the “Invasive Species” trail | No Activity | Tom Schneider
DC exhibit: Water Impact on the Refuge | No Activity | Tom Schneider
Large wall map of the BNWR | No Activity | Tom Schneider
High magnification projecting microscope | Inherited from INEOS | Ed Barrios | 0
Table-cabinet for this microscope | to be custom built to include raised platform to enable writing on TV screen | Ed Barrios
HD large format wall-mounted TV | Installed. | Ed Barrios | 1638.97
20X to 40X microscopes | Cancel. Current supply is sufficient | Ed Barrios | 0
Twenty higher quality binoculars with at least 7X35 optics | New item | Ed Barrios
Algae tank | Cancel. Our pound water once again has plenty of algae
Movie on BNWR, highlighting EE opportunities | Joe Lange contracted and he is in the process of filimg. | Tom Schneider
Estuary exhibit in a Cross Trails shelter | No Activity
Water exhibit in a Cross Trails shelter | No Activity
Geology exhibit in a Cross Trails shelter | No Activity
Pull-off parking at Cross Trails shelters | Cancel, would enroach on estuary.
Rollup shutters for Cross Trails shelters | Can't find awning maker willing to custom make tarp/clear vinyl shutters. | Phil Huxford
Interpretive signs on Otter Slough Trail | No Activity | Tom Schneider
2nd Butterfly garden, visible from lobby of DC | Plants purchased and area ready for soil | David Plunkett