## Sheet1
ATTACHMENT F
TABULAR SUMMARY
Project: Dow Woods Trails Grant #RT-907 |  | Reimbursement Request #2
Friends Project Number: 20091123 |  | Period Covered: June 1 through July 31, 2010
| Estimate | Completed Last Request | Completed This Period | Total Complete
Professional Servides (Administration, surveying, bid packages, etc.)
| 10000 | 4665.14 | 20987.54 | 25652.68
Construdtion Elements
Parking Lot | 15000 | 14574.71 | 0 | 14574.71
Southeast Trail | 60000 | 16027.12 | 39427.56 | 55454.68
Northeast Trail | 90000 | 0 | 23372.76 | 23372.76
Boardwalks | 23000 | 0 | 377.5 | 377.5
Restrooms | 30000 | 99 | 331.92 | 430.92
Bayou Crossing | 34000 |  |  | 0
Total Material and Construction Costs | 252000 | 30700.83 | 63509.74 | 94210.57
Total Project | 262000 | 35365.97 | 84497.28 | 119863.25
Note of 13Nov10: the numbers above include estimates of both cost and in-kind. The $20,000 Dow Grant is arbitriirlly included under Professional Services. This grant dollars will be re-located in future Attachment F reports.